Sprint 6 Retrospective

Team: team20-Tim-Djordjina

Repository: mrs-team20-Tim-Djordjina

Sprint 6 Dates: [17.07.2026] – [02.08.2026]

Participants: [Đorđe Malešević SV03/2021, Atina Folić SV87/2023]

Facilitator: [Đorđe Malešević SV03/2021]

Sprint Snapshot

- Committed: ~26SP -> Complited:  ~26SP (all four items delivered)

- But: Issue #25 shipped as an MVP slice of US#2.4.1; a large backlog carries to Sprint 7

- Delivered: (admin driver-registration UI), (profile + driver approval), (block/unblock), (ride request MVP)

What Went Well (Continue)

- All four committed items were delivered - each with a PR.

- First map integration (OpenStreetMap / osmdroid) - a genuinely new capability for the project, now working end to end.

- Cross-layer debugging - The team diagnosed hard, non-obvious bugs: a read-only-transaction that silently skipped a flush, Lombok recursion across JPA relationships, and a Material 2-vs-3 theme root cause. These were not easy to find.

- A prior deferral was closed - the US#2.12 block-note-on-order criterion was completed inside #25.

- Testing discipline held - integration tests accompanied the two largest stories.

What Didn't Go Well (Problems)

- Over-commitment — and now it's a pattern - ~26 SP against a ~20–26 capacity was flagged at planning, and it's the second sprint running that the team committed at/over the ceiling. It only "worked" because #25 was quietly narrowed to an MVP mid-sprint — a reactive rescue, not a plan.

- The Sprint 5 spike lesson was not applied - The last retro's headline action was "time-box a spike for unfamiliar integrations." This sprint the theme (Material 2/3) and map (OSM tile policy) integrations ate real time — exactly the failure that lesson was meant to prevent.

- A recurring action item is now three sprints old - The local-dev setup guide has been an action item since Sprint 4, reaffirmed in Sprint 5, and still doesn't exist.

- Estimation misses again - #23 was 3 SP for what was really 5–8 (the approval workflow); #25's true §2.4.1 scope is far beyond its 13 SP.

- Environment/integration friction dominated - parts of the sprint (theme visibility, OSM 403s, device-specific crashes) rather than feature logic.

What We Learned

Process (the recurring theme)

- Action items that aren't owned, dated, and verified simply recur - The local-dev doc has been "an action item" three times without a name against it. Listing isn't doing.

- MVP scope should be a planning decision, not a mid-sprint discovery - Narrowing #25 was the right call - but deciding it up front would have made the commitment honest from day one.

- Epics must be broken into sized sub-stories before being committed - Carrying US#2.4.1 as one 13 SP lump (really 30+) guaranteed a large, blurry carryover.

Technical

- `@Data` on bidirectional JPA entities generates recursive `toString`/`equals` → `StackOverflowError`; exclude relationship fields. (This bit *twice* — caught in review for `Ride`/`RideStop`, in running code for `Driver`/`Vehicle`.)

- `@Transactional(readOnly = true)` silently skips the flush, so writes don't persist; and a self-invoked `@Transactional` method doesn't get its own transaction.

- OpenStreetMap's tile policy blocks default (`com.example`) user agents and throttles some IPs — map providers need a spike and a fallback.

Start / Stop / Continue

| Start | Stop | Continue |
| --- | --- | --- |
| Deciding MVP scope at planning, not mid-sprint | Committing at/over capacity (now 2 sprints running) | Methodical cross-layer debugging |
| Breaking epics into sized stories before committing | Re-listing the same action items without owning them | Integration tests alongside features |
| Assigning owner + due date + verification to every action item | Estimating epics as a single lump | A PR per issue |
| Spiking unfamiliar integrations (notifications, routing) before the dependent story | — | Closing prior deferrals |

Team Sentiment

| Member | Mood (1-5) | One word |
| --- | --- | --- |
| Djordje Malesevic SV03/2021 | 4 | Great |
| Atina Folic SV87/2023 | 4 | Great |