Sprint 6 Review

Team: team20-Tim-Djordjina

Repository: mrs-team20-Tim-Djordjina

Sprint 6 Dates: [17.07.2026] – [02.08.2026]

Participants: [Đorđe Malešević SV03/2021 (1), Atina Folić SV87/2023 (2)]

[Scrum Master -> 1][Product Owner -> 2]

1. Sprint Goal

Close out the remaining account/admin UI work (profile, admin driver onboarding, driver management) and begin the core ride-hailing feature — requesting a ride.

Outcome: All four committed items were delivered. The three account/admin stories are complete. The ride-request feature works end to end, but as an MVP slice of US#2.4.1 — a large amount of that specification (scheduling, reminders, advanced matching, notifications, ride execution) now carries to Sprint 7.

2. Sprint Backlog & Status

| Item | Description | Spec | SP | Status |
| --- | --- | --- | --- | --- |
| #19 | In-app admin driver-registration screen | US#2.2.3 UI | 5 | ✅ Done |
| #21 | Admin block/unblock users with notes | US#2.12 | 5 | ✅ Done |
| #23 | User profile + driver change approval | US#2.3 | 3 | ✅ Done |
| #25 | Ride request (MVP) | US#2.4.1 | 13 | ✅ Done |

3. Velocity Summary

- Committed: ~26 SP

- Completed: ~26 SP (all four items)

- Sprint completion: 100% of committed items

The commitment (~26 SP) was flagged at planning as at/above a realistic 20–26 SP capacity. It was delivered only because #16 was deliberately scoped as an MVP rather than the full US#2.4.1 — the complete ride feature is materially larger than 13 SP and is now spread across the Sprint 7 backlog. Story points were "completed," but the underlying feature is not finished.

4. Sprint Review Demo

Demonstrated to stakeholders:

1. Profile (US#2.3): view/edit personal details; a driver's edit is submitted for approval (not applied); an admin approves it and the change becomes visible; change password; logout.

2. Admin driver registration (US#2.2.3): an admin registers a driver + vehicle from the app; the driver receives a set-password email, sets a password, and logs in.

3. Admin block/unblock (US#2.12): admin blocks a user with a note; the blocked user can't log in; a blocked driver is excluded from assignment; a blocked passenger sees the note when ordering.

4. Request a ride (US#2.4.1 MVP): on an OpenStreetMap map, tap pickup/destination/stops, choose vehicle type + baby/pet, submit → the system computes the fare, assigns the nearest eligible driver, and shows the result.

5. Completed Work (Detail)

- Issue #19 - Admin Driver-Registration Screen (US#2.2.3)

In-app UI over the existing admin endpoint: driver + vehicle form, validation, ADMIN-only access, success/error handling.

- Issue #21 - Admin Block/Unblock with Notes (US#2.12)

Backend list/block/unblock endpoints + Android screen. Blocked login and blocked-driver exclusion reuse existing `canLogin()` / `canAcceptRides()`. Block note shown on the user's row.

- Issue #23 - User Profile + Driver Change Approval (US#2.3)

View/edit, change password, logout; drivers see 24h working minutes + vehicle. Driver edits create a pending `ProfileChangeRequest`; admins approve/reject via a dedicated screen. Integration tests included.

- Issue #25 - Ride Request (MVP) (US#2.4.1)

`Ride`/`RideStop` model, fare (`base + km × 120`), Haversine distance over pickup → ordered stops → destination, nearest-eligible-free-driver matching, blocked-rider rejection with note, no-driver 409. Android map screen (osmdroid/OpenStreetMap) with the assignment result. Integration tests included. Driver becomes available on login (US#2.2.1).

6. Acceptance Criteria Verification

#19 - [x] admin registers a driver in-app; [x] validation; [x] duplicate email/plate surfaced; [x] ADMIN-only

#21 - [x] list/block/unblock; [x] note required; [x] blocked user can't log in; [x] blocked driver not assigned; [x] note shown on order

#23 - [x] view/edit; [x] driver edits pending approval; [x] admin approve/reject; [x] driver hours + vehicle; [x] change password; [x] logout

#25 - [x] request with ordered stops; [x] vehicle type + baby/pet filtering; [x] fare = base + km×120; [x] nearest eligible driver; [x] 8h/blocked/busy excluded; [x] no-driver rejection; [x] blocked passenger 403 + note

- [ ] Full §2.4.1 (scheduling, reminders, advanced matching, linked passengers, notifications) — carried to Sprint 7

7. Challenges & Resolutions

| Challenge | Resolution |
| --- | --- |
| Material 3 switches invisible in light mode; a `SwitchCompat` crash | Root cause: light theme used a Material 2 parent while night used Material 3. Migrated the light theme to Material 3 and replaced switches with `CheckBox` + explicit tint. |
| OpenStreetMap MAPNIK tiles blocked (403) | OSM blocks the default `com.example` user agent and throttled the device; switched the tile source to OpenTopoMap (still OSM-based). |
| `StackOverflowError` saving a driver | `@Data` generated recursive `toString`/`equals` across `Driver`↔`Vehicle`↔`User`; excluded relationship fields with `@ToString.Exclude` / `@EqualsAndHashCode.Exclude`. |
| Driver availability flags not persisting on login | `loginUser` was `@Transactional(readOnly = true)` (and the nested call was a self-invocation), so writes were never flushed; made login a read-write transaction. |
| Ride stops not saved + wrong distance | Missing stop-persistence loop and a `getDestinationLatitude()` typo in `buildRoute`; both fixed. |

8. Incomplete / Carryover Items (Sprint 7 backlog)

- Busy-driver matching (nearest to pickup + ~10 min from finishing) — MVP matches free drivers only

- Scheduling up to 5h ahead + priority; reminders (15 min / every 5 min)

- Linked passengers by email (US#2.4.2); favourite routes (US#2.4.3)

- Persisted notifications (US#3.x) — the MVP returns the outcome inline

- OSM routing for real road distances — MVP uses straight-line (Haversine)

- Ride execution (start/finish) not built yet, so an assigned driver stays busy until reset; the US#2.6.1 "active passenger can't reorder" rule will be enforced with that issue

- Full driver-state management (manual active/inactive toggle, logout guard mid-ride) tracked with US#2.2.1

- No address geocoding or my-location on the map; addresses default to tapped coordinates

9. Next Sprint Preview (Sprint 7 — proposed)

- Ride execution: start / finish (US#2.6–2.7)

- Busy-driver matching, scheduling, reminders

- Persisted notifications (US#3.x)

- OSM routing for real distances