Sprint 5 Retrospective

Team: team20-Tim-Djordjina

Repository: mrs-team20-Tim-Djordjina

Sprint 5 Dates: [03.07.2026] – [12.07.2026]

Participants: [Đorđe Malešević SV03/2021, Atina Folić SV87/2023]

Facilitator: [Atina Folić SV87/2023]

Sprint Snapshot

- Committed: ~18 SP → Completed: ~15 SP (~83%)

- Delivered: Issues #10 (JWT endpoint security), #11 (password reset with deep link), #12 (admin driver registration) — all with integration tests

- Carryover: Android Profile screen (3 SP)

- Overall: the authentication/security goal was fully met; one supporting UI item slipped

What Went Well (Continue)

- The sprint goal was delivered. All three committed auth/backend stories shipped, each with automated tests — a solid, secured authentication system.

- Design reuse over duplication. The password-reset mechanism was reused for driver onboarding (set-password link), avoiding a second bespoke flow.

- Testing discipline improved. Two new integration-test suites this sprint exercise the real security stack (JWT security; admin registration), not just happy paths.

- Methodical debugging. The email deep-link problem was isolated cleanly — using adb to prove the intent-filter worked, which pinpointed the email client (not the app) as the cause.

- Reviews caught real issues early — test mocking approach, the ROLE_ prefix, and entity relationships in tests were fixed before merge.

What Didn't Go Well (Problems)

- The Profile screen slipped. The deep-link/email investigation in Issue #13 quietly consumed the time budgeted for Profile, and it carried over.

- Under-estimated unknowns. "Password reset with deep link" was estimated like normal work, but it contained real unknowns (custom-scheme behavior in Gmail, deep-link setup) that weren't accounted for.

- UI work trailed backend again. This is now a recurring pattern (also seen in Sprint 4) — the Android piece is consistently the part that gets squeezed.

- Recurring environment friction. Small setup snags again (e.g. adb not on PATH, deep-link testing). Minor individually, but they keep recurring — and the local-dev setup guide from the Sprint 4 retro doesn't appear to exist yet.

What We Learned

Process

- Stories with genuine unknowns (a new integration, a third-party behavior) should be spiked or time-boxed separately before the dependent work is committed — otherwise the unknown silently eats another story.

- When backend and UI live in one story, the UI is the part that slips under pressure; splitting them (or pairing earlier) protects it.

Technical

- Email clients strip custom-scheme (rideon://) links — a normal HTTP link that 302-redirects into the app is needed; verify the deep link itself with adb independent of email.

- Spring Boot 3.5 testing specifics: @MockitoBean replaces @MockBean; mock injected dependencies correctly; set entity relationships through the object graph.

- The hasRole("ADMIN") / ROLE_ADMIN prefix contract must be verified end-to-end (an integration test guards it).

Follow-through

- Retro action items only help if they're actually done — recurring environment friction suggests Sprint 4's "local dev setup doc" and secret-scanning items need a real owner and due date this time.

Start / Stop / Continue

| Start | Stop | Continue |
| --- | --- | --- |
| Time-boxing a spike for any unfamiliar integration | Committing dependent UI work behind un-spiked unknowns | Writing integration tests alongside features |
| Pulling UI work earlier / pairing on the Android side | Letting investigation time silently consume a story's budget | Methodical, cross-layer debugging (e.g. adb isolation) |
| Actually writing the local-dev setup guide (carried from Sprint 4) | Estimating unknowns as if they were routine | Reusing existing mechanisms instead of rebuilding |
| Reviewing previous retro action items at planning | - | Thorough, defect-catching code reviews |

Team Sentiment

| Member | Mood (1-5) | One word |
| --- | --- | --- |
| Đorđe Malešević SV03/2021 | 4 | Great |
| Atina Folić SV87/2023 | 4 | Great |