Sprint 5 Review

Team: team20-Tim-Djordjina

Repository: mrs-team20-Tim-Djordjina

Sprint 5 Dates: [03.07.2026] – [12.07.2026]

Participants: [Đorđe Malešević SV03/2021 (1), Atina Folić SV87/2023 (2)]

[Scrum Master -> 2][Product Owner -> 1]

1. Sprint Goal

Complete and secure the authentication system (endpoint protection + password reset), and deliver admin-driven driver onboarding, building on the login/JWT work from Sprint 4.

Outcome: The security and authentication goals were fully met. Admin driver registration (backend) was delivered. The one supporting UI item (Android Profile screen) was not completed and carries over.

2. Sprint Backlog & Status

| Item | Description | SP | Status |
| --- | --- | --- | --- |
| Issue #13 | Secure protected endpoints (JWT filter) | 5 | ✅ Done |
| Issue #15 | Password Reset with email deep link (US#2.2.1_2) | 5 | ✅ Done |
| Issue #17 | Driver Registration by Admin — backend (US#2.2.3) | 5 | ✅ Done |
| — | Android Profile screen | 3 | ⏳ Carryover |

3. Velocity Summary

- Committed: ~18 SP

- Completed: ~15 SP (Issues #13, #15, #17)

- Carryover: 3 SP (Android Profile screen)

- Sprint completion: ~83% of committed work

The three authentication/backend stories were completed with automated tests. The Profile screen slipped, partly because the email deep-link work in Issue #15 took more investigation than estimated.

4. Sprint Review Demo

Demonstrated to stakeholders:

- Endpoint security (Postman): a protected route returns 401 without a token and 200 with a valid token; an admin-only route returns 403 for a USER token and succeeds for an ADMIN token.

- Password reset (end-to-end on a real device): "Forgot password?" → email arrives → tap the link → the app opens the reset screen → set a new password → log in with it (old password no longer works).

- Admin driver registration (Postman → device): admin registers a driver with vehicle details → the driver receives a "set your password" email → taps the link → sets a password → logs in as a driver.

5. Completed Work

Issue #13 — JWT Endpoint Security

- JwtAuthenticationFilter (validates the Bearer token, sets the security context with the user's role).

- SecurityConfig updated: /api/auth/** public, /api/admin/** ADMIN-only, everything else authenticated; clean 401/403; stateless sessions.

- GET /api/users/me protected endpoint (for the upcoming Profile screen).

- Android: SessionExpiredInterceptor clears the session and returns to login on a 401.

- Integration tests (JwtSecurityIntegrationTest, 7 tests) + an H2 test profile.

Issue #15 — Password Reset with Deep Link

- Backend: forgot-password and reset-password endpoints, 1-hour single-use token, Gmail-SMTP reset email.

- reset-redirect endpoint that 302-redirects an HTTP link to the rideon:// deep link (so email clients keep the link tappable).

- Android: Forgot Password and Reset Password screens; deep-link intent-filter and token parsing; login-screen link.

- Verified end-to-end on a real device.

Issue #17 — Driver Registration by Admin (Backend)

- POST /api/admin/drivers (ADMIN-only) creating User (DRIVER) + Driver + Vehicle in one transaction.

- Driver sets their own password via a reused set-password link (admin never sets it); 24-hour token.

- Unique email and license-plate validation.

- Integration tests (AdminDriverRegistrationIntegrationTest, 6 tests: 201 + persistence, 403, 401, 409, 400 duplicate plate, 400 validation).

6. Acceptance Criteria Verification

Issue #13

- No token → 401; invalid token → 401; valid token → 200

- Wrong role → 403; correct role → allowed

- Public auth endpoints stay reachable

- Android handles 401 by clearing session and returning to login

Issue #15

- Request reset by email; 1-hour single-use token

- Reset email delivered with a tappable link that opens the app

- New password works; old password rejected; reused/expired token rejected

Issue #17

- Admin creates a driver with vehicle info (ADMIN-only)

- Driver receives a set-password email, sets a password, and logs in

- Duplicate email/plate rejected; transactional creation (no orphans)

Android Profile screen

- Not completed — carried to Sprint 6

7. Challenges & Resolutions

| Challenge | Resolution |
| --- | --- |
| Email deep link didn't open from Gmail (custom rideon:// scheme stripped by the client) | Added a public /api/auth/reset-redirect HTTP endpoint that 302-redirects to the deep link; the email now uses a tappable HTTP link. Verified the deep link itself with adb ... am start. |
| JWT ROLE_ prefix mismatch risk (hasRole("ADMIN") expects ROLE_ADMIN) | Filter builds ROLE_ + role; the integration test's admin-success case guards against regressions. |
| Unit-test mocking questions (PasswordEncoder as injected dependency; @MockBean deprecated in Spring Boot 3.5) | Mocked injected dependencies correctly and moved to @MockitoBean; fixed the Driver–User test setup to use the entity relationship. |
| Tests needed a database without touching PostgreSQL | Added an H2-based test profile (application-test.properties), committed since it holds no secrets. |
| Windows/PowerShell adb not on PATH | Ran via .\adb from platform-tools (or add it to PATH) — environment-only, no code impact. |

8. Next Sprint Preview (Sprint 6)

- Android Profile screen (carryover)

- In-app admin driver-registration screen (deferred from Issue #12; admin currently uses Postman/web)

- Ride operations (US#2.3.x)

- Admin driver management (list / block / edit)