Sprint 8 Retrospective

Team: team20-Tim-Djordjina

Repository: mrs-team20-Tim-Djordjina

Sprint 8 Dates: [11.08.2026] – [16.08.2026]

Participants: [Đorđe Malešević SV03/2021, Atina Folić SV87/2023]

Facilitator: [Đorđe Malešević SV03/2021]

Sprint Snapshot

- Delivered: ~29 SP → six features (#41, #43, #45, #47, #49, #51) each with backend, tests, Android, and a PR

- Capacity: ~20 SP

- Deferred on purpose: routing, local-dev doc, rider panic UI

What Went Well (Continue)

- Reasoned scope management. The deferrals were justified - routing for spike-first risk, rider panic for a real US#2.6.2 dependency, local-dev doc as debt. This is the calibration maturity Sprints 5–7 lacked: trade-offs, not heroics.

- The recurring gotcha was handled proactively. The Sprint 7 DoD item ("new enum value → widen the constraint") worked — PANIC was anticipated at planning, not discovered at runtime. First time a recurring problem was solved by the process rather than rediscovered.

- Deliberate reuse kept effort down - #49 reused #41 via an extracted RideHistoryMapper; #51 built on #27/#29. High output for the points because the team leaned on existing work.

- Testing + PR discipline held through a stretched, deadline-driven sprint.

- Real bugs were tracked to root cause - the missing notifyDataSetChanged() (via logging, not guessing) and a request-race guard.

What Didn't Go Well (Problems)

- The local-dev guide slipped for this sprint. The Sprint 7 mechanism (named owner + reserved debt slot) did not survive deadline pressure.

- Scope grew mid-sprint. #49 and #51 were added after planning. Reasoned and reuse-heavy, yes — but adding to a sprint mid-flight is the old over-commit habit in new clothes, and it means planning didn't capture the real priorities.

- A dependency was discovered mid-build, not at planning. Rider panic's need for the US#2.6.2 tracking screen surfaced while implementing, forcing a mid-sprint deferral. A dependency spike would have caught it earlier.

- Still over capacity.

What We Learned

Process — the reframe

- Calibration was never beyond the team. The reasoned deferrals prove it can weigh risk and dependency and choose. Combined with Sprint 7 (which proved capability), the honest conclusion across Sprints 5–8 is: neither capability nor calibration was ever the real constraint — deadline pressure is. The remaining over-capacity is a conscious choice, not a failing.

Process — dependencies belong at planning

- Mid-sprint scope additions and mid-build dependency discoveries both point at the same gap: planning didn't fully map priorities or prerequisites. A short dependency pass at planning would have flagged rider panic → US#2.6.2 up front.

Technical

- Any change to an adapter's backing list needs a notify… call — a missing notifyDataSetChanged() shows stale rows.

- Overlapping async requests need a sequence/latest-wins guard so a slow earlier response can't overwrite the current one.

- OS process-lifecycle logcat noise ("refused to die") is not an app bug — read for the real FATAL EXCEPTION instead.

Start / Stop / Continue

| Start | Stop | Continue |
| --- | --- | --- |
| Doing the recurring debt item local-dev setup first, before any feature work | Adding scope mid-sprint (pull from a ranked backlog at the checkpoint instead) | Reasoned, deliberate deferrals |
| A dependency pass at planning (would have caught rider panic → US#2.6.2) | Re-adding local-dev setup every retro without changing the mechanism | The enum→constraint DoD habit |
| Naming when over-capacity is a deliberate deadline choice vs. drift | Treating the deadline as a reason to skip calibration entirely | Deliberate reuse; end-to-end tests + a PR per issue |

Team Sentiment

| Member | Mood (1–5) | One word |
| --- | --- | --- |
| Đorđe Malešević SV03/2021 | 4 | Great |
| Atina Folić SV87/2023 | 4 | Great |